## Main Floor
Openhouse 2026 Robotlist
S.No. | Robot Model | Application | IP Address
1 | CRX-10iA/L | Experience Centre | NA
2 | CRX-10iA/L | Order Fulfilment Cell | 10.31.58.72
3 | CRX-10iA/L | Nut Tightening Cell | 10.31.58.73
4 | CRX-20iA/L | CRX Force Control Cell | 10.31.58.74
5 | CRX-30iA | Bucket Palletizing Cell | 10.31.58.75
6 | CRX-5iA | CRX Lineup | 10.31.58.76
7 | CRX-3iA |  | 10.31.58.77
8 | CRX-10iA/L |  | 10.31.58.78
9 | CRX-20iA /L |  | 10.31.58.79
11 | SR-3iA | High Speed Pick and Place Cell | 10.31.58.80
12 | SR-20iA | High Speed Secondary Packaging Cell | 10.31.58.81
13 | LR-Mate 7-9D | AI Error Proofing Cell | 10.31.58.82
14 | M-20iD 35 | Intelligent Bin Picking Cell | 10.31.58.83
15 | CRX-10iA/L | CRX-Paint Cell | 10.31.58.84
16 | P50iB/10L | Paint Cell | NA
17 | LR-Mate 200iD/7L | Deburring Cell | 10.31.58.86
18 | R-2000iC 270F | Drilling Cell | 10.31.58.87
19 | R-2000iC 210F | RTU Cell | 10.31.58.88
20 | M-900iB 360 | Fixtureless Welding Cell | 10.31.58.1
21 | Arc Mate 120iD 12L |  | 10.31.58.3
22 | M20iD 25 |  | 10.31.58.2
23 | CRX 5iA | AMR Setup | NA
24 | M-410iC/185 | High Speed Palletizing | 10.31.58.92
25 | M-710iD/70 | AI Palletizing Cell | 10.31.58.93
26 | M-2iA/35L | High Speed Primary Packaging Cell | 10.31.58.94
27 | CRX-10iA/L | RTVT
28 | M-10iD 12 | Robotic Grinding Cell
29 | CRX-10iA/L | Collaborative Arc Welding | 192.168.0.1
30 | Arc Mate 100iD | Adaptive arc welding | 192.168.1.2
31 | Arc Mate 120iD | Cladding Cell | 192.168.1.20
32 | R-2000iC 165F | Dispensing Cell | UNASSIGNED

## Fusion Hub (hidden)
Fusion Hub
S.No. | Robot Model | Application | Primary | Secondary | Remarks
27 | Arc Mate 120iD | Adaptive Aluminium Welding Cell | Kaushik Golla | Ciril Joy Kochu T | • Set up needs to be moved
28 | Arc Mate 100iD | Adaptive Arc Welding System | Ciril Joy Kochu T | Himanshu Sharma | • Set up needs to be moved
29 | CRX-10iA/L | Collaborative Arc Welding System | Himanshu Sharma | Roshan S | • Set up needs to be moved
30 | CRX-3iA | Collaborative Arc Welding System | Roshan S | Ekamjit Singh | • Set up needs to be moved

## TC Running Status (hidden)
Tech Center Running Status |  |  |  |  | Date:
Sl.No. | Robot Model | Application | Primary | Secondary | Status
1 | CRX-10iA/L | Experience Centre | AAYUSH | HARISH
2 | CRX-10iA/L | Order Fulfilment Cell | KARTHIK | TANUSHREE
3 | CRX-10iA/L | Nut Tightening Cell | HARISH | DHIRAJ
4 | CRX-20iA/L | CRX Force Control Cell | TANUSHREE | AAYUSH
5 | CRX-30iA | Bucket Palletizing Cell | DHIRAJ | KARTHIK
6 | CRX-5iA | CRX Lineup | AAYUSH | TANUSHREE
7 | CRX-10iA
8 | CRX-10iA/L
9 | CRX-20iA/L
10 | CRX-30iA
11 | SR-3iA | High Speed Pick and Place Cell | KARTHIK | DHIRAJ
12 | SR-20iA | High Speed Secondary Packaging Cell | HARISH | AAYUSH
13 | LR-Mate 200iD/7L | AI Error Proofing Cell | TANUSHREE | KARTHIK
14 | M-20iD 35 | Intelligent Bin Picking Cell | DHIRAJ | HARISH
15 | CRX-10iA/L | CRX-Paint Cell | AAYUSH | DHIRAJ
16 | P50iB/10L | Paint Cell | KARTHIK | AAYUSH
17 | LR-Mate 200iD/7L | Deburring Cell | HARISH | TANUSHREE
18 | R2000iC/270F | Drilling Cell | TANUSHREE | HARISH
19 | R2000iC/210F | RTU Cell | DHIRAJ | TANUSHREE
20 | M-900iB 360 | Fixtureless Welding Cell | AAYUSH | KARTHIK
21 | CRX 5iA | AMR Setup | KARTHIK | HARISH
22 | M-410iC/185 | High Speed Palletizing | HARISH | DHIRAJ
23 | M-710iD/70 | AI Palletizing Cell | TANUSHREE | AAYUSH
24 | M-2iA/35L | High Speed Primary Packaging Cell | DHIRAJ | KARTHIK
25 | CRX-10iA/L | RTVT | AAYUSH | HARISH
26 | R2000iC | Dispensing Cell | KARTHIK | TANUSHREE
27 | LR Mate 200iD/7L | Vibrator Sorting cell | HARISH | DHIRAJ
28 | Arc Mate 120iD | Adaptive Aluminium Welding Cell | TANUSHREE | AAYUSH
29 | Arc Mate 100iD | Adaptive Arc Welding System | DHIRAJ | KARTHIK
30 | CRX-10iA/L | Collaborative Arc Welding System | HARISH | AAYUSH
31 | CRX-3iA | Collaborative Arc Welding System | KARTHIK | TANUSHREE
32 | ER4iA | Education Kit | HARISH | DHIRAJ
33 | ZDT Display | TV Display | TANUSHREE | AAYUSH
34 | VR Display | TV Display | DHIRAJ | KARTHIK
35 | Roboguide Display | TV Display | HARISH | AAYUSH
36 | R50iA Controller Display | TV Display | KARTHIK | TANUSHREE

## TC Pending material Procurment (hidden)
Tech center cell pending points
S.No. | Robot Model | Application | Target date | Primary | Secondary | As on 04-05-2026 | As on 29-04-2026 | Remarks | Action Plan | Design requirement | As on 17-04-2206
1 | CRX-10iA/L | Experience Centre | 46142 | AAYUSH | HARISH | Waiting for quotation from the vendor, expected to receive by 29-04-2026, PR will be released by 30-04-2026. | Waiting for quotation from the vendor, expected to receive by 29-04-2026, PR will be released by 30-04-2026. | • Cable tray for wire routing required - Need to procure • Front/Back covers need to be changed - Need to procure • Name plates ordered — need to be replaced | Side cover Drawing need to take from design team - 14-04-2026 PR neeed to be released by 14-04-2026 Name plate sticker Material expected to receive by 13-04-2026 CRX name sticker need to procure - PR will be released by 14-04-2026 | Side cover design need to modify & release the PR Side cover design will receive by 21-04-2026 - | Side cover design need to modify & release the PR Side cover design will receive by 21-04-2026 -
2 | CRX-10iA/L | Order Fulfilment Cell | 46150 | KARTHIK | TANUSHREE | Vendor discussion in progress - cable tray will sent for rework by 30-04-2026 | Vendor discussion in progress - cable tray will sent for rework by 30-04-2026 | • Cable tray for wire routing required - Need to procure | Cable Tray Drawing need to take from design team - 14-04-2026 PR neeed to be released by 14-04-2026
3 | CRX-10iA/L | Nut Tightening Cell | 46150 | HARISH | DHIRAJ | Need to discuss with avinash, from Japan Tool is coming by 30-04-2026. | Need to discuss with avinash, from Japan Tool is coming by 30-04-2026. | • Contact Avinash sir for controller & tool change • Cable tray for wire routing required - Need to procure • Programming need to start after assembling the tool. • Front/Back covers need to be changed - Need to procure | Nutrunner tool & controller - Need to get details from Esstic vendor Side cover Drawing need to take from design team - 14-04-2026 PR neeed to be released by 14-04-2026 Cable Tray Drawing need to take from design team - 14-04-2026 PR neeed to be released by 14-04-2026 | Nutrunner tool & controller - Need to get details from Esstic vendor Side cover Drawing need to take from design team - 14-04-2026 PR neeed to be released by 14-04-2026 Cable Tray Drawing need to take from design team - 14-04-2026 PR neeed to be released by 14-04-2026 | Need to discuss with avinash
4 | CRX-20iA/L | CRX Force Control Cell | 46150 | TANUSHREE | AAYUSH | Side cover design need to modify & release the PR | Side cover design need to modify & release the PR | • Program touch-up required • Change name plate - Need to procure • Front/Back covers need to be changed - Need to procure | Name plate sticker Material expected to receive by 13-04-2026 Side cover Drawing need to take from design team - 14-04-2026 PR neeed to be released by 14-04-2026 Cable Tray Drawing need to take from design team - 14-04-2026 PR neeed to be released by 14-04-2026 | Side cover design need to modify & release the PR | Side cover design need to modify & release the PR
5 | CRX-30iA | Bucket Palletizing Cell | 46144 | DHIRAJ | KARTHIK | Assistive Concept discussion with team completed on 17-04-2026. Component - 40KG Dumble - Design & Release EPOS crain vendor will visit for showcasing Crane demo, need to check electrical connection & communication protocal. | Assistive Concept discussion with team completed on 17-04-2026. Component - 40KG Dumble - Design & Release EPOS crain vendor will visit for showcasing Crane demo, need to check electrical connection & communication protocal. | • Program touch-up required • Cell need to be shifted as per the TC Layout • Name plates - Need to procure Assistive load upgradation need to be implemented. | Name plate sticker Material expected to receive by 13-04-2026 Cell shifting will be done by 24-04-2026 Need to collect details from Arunkumar. | Concept is ready need to discuss with team. Quotation need to shared with team by 17-04-2026. Meeting ned to arrange on 17-04-2026 with design team. | Assistive Concept discussion with team completed on 17-04-2026. Component - 40KG Dumble - Design & Release EPOS crain vendor will visit for showcasing Crane demo, need to check electrical connection & communication protocal.
6 | CRX-5iA |  | 46132 |  |  | Need to call vendor & release PR for Wooden Door. | Need to call vendor & release PR for Wooden Door. | • CPU updated. | Covers need to plan for Controller opening space - Inprogress. Will discuss with vendor & finalise | Covers need to plan for Controller opening space - Inprogress. Will discuss with vendor & finalise | Need to call vendor & release PR for Wooden Door.
7 | CRX-10iA |  |  |  |  | Vendor is not responding | Vendor is not responding | Cover need to procure
8 | CRX-10iA/L | CRX Lineup |  | AAYUSH | TANUSHREE |  |  | • Covers need to be changed - (Need to plan)
9 | CRX-20iA/L
10 | CRX-30iA
11 | SR-3iA | High Speed Pick and Place Cell | 46142 | KARTHIK | DHIRAJ | Vendor discussion in progress - cable tray will sent for rework by 30-04-2026 | Vendor discussion in progress - cable tray will sent for rework by 30-04-2026 | • Noise issue, needs greasing, sanding of lead screw. • Spare component needed (Need to verify). • CPU positioning • Cable tray & routing • Confirm if common display works for both SCARA robots (if not, get 2x TV & Stand) | Cable tray re-coating need to be done - PR will be released by 13-04-2026. | Cable tray re-coating need to be done - PR will be released by 13-04-2026. | Cable tray re-coating need to be done - PR will be released by 13-04-2026.
12 | SR-20iA | High Speed Secondary Packaging Cell | 46142 | HARISH | AAYUSH | Vendor discussion in progress - cable tray will sent for rework by 30-04-2026 | Vendor discussion in progress - cable tray will sent for rework by 30-04-2026 | • Speed need to be modified • Base Mounting Screw need to be replaced. • Count & manage cans component | Cable tray re-coating need to be done - PR will be released by 13-04-2026. | Cable tray re-coating need to be done - PR will be released by 13-04-2026. | Cable tray re-coating need to be done - PR will be released by 13-04-2026.
13 | LR-Mate 200iD/7L | AI Error Proofing Cell | 46142 | TANUSHREE | KARTHIK | Points closed | Points closed | • CPU positioning • Cable routing | Cable tray re-coating need to be done - PR will be released by 13-04-2026. | Cable tray re-coating need to be done - PR will be released by 13-04-2026. | Name plates need to add in the cell
14 | M-20iD 35 | Intelligent Bin Picking Cell | 46142 | DHIRAJ | HARISH | Programming support requested to Expert team, waiting for reply Vendor discussion in progress - cable tray will sent for rework by 30-04-2026 | Programming support requested to Expert team, waiting for reply Vendor discussion in progress - cable tray will sent for rework by 30-04-2026 | • Finger change • Program update need to verify | Programming support requested to Expert team, waiting for reply Cable tray re-coating need to be done - PR will be released by 13-04-2026. | Programming support requested to Expert team, waiting for reply Cable tray re-coating need to be done - PR will be released by 13-04-2026. | Programming support requested to Expert team, waiting for reply Cable tray re-coating need to be done - PR will be released by 13-04-2026.
15 | CRX-10iA/L | CRX-Paint Cell | 46142 | AAYUSH | DHIRAJ | Red colour Pigment received, vendor need to find for re-coating. | Red colour Pigment received, vendor need to find for re-coating. | • Component recoating - Need to send for re-coating Display Need to plan Monitor need to plan | Component recoating - PR will be released by 14-05-2026. Need to get delivery date. pigment will be ordered by 14-08-2026 | Red colour Pigment | Red colour Pigment
16 | P50iB/10L | Paint Cell | 46120 | KARTHIK | AAYUSH | Yellow Colour pigment received. Vendor need to find for re-coating. 2L primer | Yellow Colour pigment received. Vendor need to find for re-coating. 2L primer | • New component, recoating - Need to send for re-coating • EOAT - UV light need to plan | Component recoating Colour need to finalised by 13-04-2026 Need to get delivery date. EOAT UV light need to plan & PR need to be relased. | Yellow Colour pigment 2L primer | Yellow Colour pigment 2L primer
17 | LR-Mate 200iD/7L | Deburring Cell | 46142 | HARISH | TANUSHREE | PR will be released by 30-04-2026. | PR will be released by 30-04-2026. | • Acrylic sheet needs to be replaced Name plate need to verify | • Acrylic sheet needs to be replaced - PR will be released by 14-05-2026 | • Acrylic sheet needs to be replaced - PR will be released by 14-05-2026 | Need to collect drawing from design team
18 | R2000iC/270F | Drilling Cell | 46129 | TANUSHREE | HARISH | Spare Drill bit released - 03 Nos. Expected to receive by 04-05-2026. | Spare Drill bit released - 03 Nos. Expected to receive by 04-05-2026. | • Programming needs to be done Name plate - Need to procure Monitor positioning need to be changed Fence layout need to change | Name plate sticker will be released by 14-04-2026 Monitor positioning & Fence assembly modification will be done by 14-04-2026. Oil Holder stand for tool. | Oil Holder stand for tool. | Oil Holder stand for tool - 20-04-2026. Spare Drill bit need to order for Drilling cell - 10Nos.
19 | R2000iC/210F | RTU Cell | 46132 | DHIRAJ | TANUSHREE | RSP Ethernet cable connection issue. Need to replace the cable. RSP will reply by 14-04-2025, need to plan according to that. Name plate need to release Fixture & Component need to change New* product RTU & RTVT Nameplate Details about RTU Unit - Board | RSP Ethernet cable connection issue. Need to replace the cable. RSP will reply by 14-04-2025, need to plan according to that. Name plate need to release Fixture & Component need to change New* product RTU & RTVT Nameplate Details about RTU Unit - Board | • Meeting to be arranged with Avinash sir and vendor; - 07-04-2026 • Name plates - Need to procure • ATC communication issue - Need to call RSP Vendor | Name plate sticker will be released by 17-04-2026 Cell building in progress expected to complete by 17-04-2026 | RSP Ethernet cable connection issue. Need to replace the cable. RSP will reply by 14-04-2025, need to plan according to that. | RSP Ethernet cable connection issue. Need to replace the cable. RSP will reply by 14-04-2025, need to plan according to that. Name plate need to release Fixture & Component need to change New* product RTU & RTVT Nameplate Details about RTU Unit - Board
20 | M-900iB 360 | Fixtureless Welding Cell | 46142 | AAYUSH | KARTHIK | • Cable routing | • Cable routing | • Name plates • Cable routing | Name plate sticker will be released by 17-04-2026 |  | • Cable routing
21 | CRX 5iA | AMR Setup | 46150 | KARTHIK | HARISH | Gripper will be arrange from Improd by dhanasekar. Gripper is coming from P&P design need to received - M/C tending application. 1st station - 3jaw gripper assembly. 2nd station - Gear matching & P&P. TP Bracket | Gripper will be arrange from Improd by dhanasekar. Gripper is coming from P&P design need to received - M/C tending application. 1st station - 3jaw gripper assembly. 2nd station - Gear matching & P&P. TP Bracket | • Set up needs to be completed EOAT need to be planned TP Bracket P&P assembly | EOAT Design details need to collect from 14-05-2026. PR need to release by 16-04-2026. P&P Fixture Design details need to collect from 14-05-2026. PR need to release by 16-04-2026 | Gripper will be arrange from Improd by dhanasekar. P&P design need to received - M/C tending application. 1st station - 3jaw gripper assembly. 2nd station - Gear matching & P&P. TP Bracket | Gripper will be arrange from Improd by dhanasekar. P&P design need to received - M/C tending application. 1st station - 3jaw gripper assembly. 2nd station - Gear matching & P&P. TP Bracket
22 | M-410iC/185 | High Speed Palletizing | 46129 | HARISH | DHIRAJ |  |  | • Bags to be replaced Cable Routing need to be done | Component replacement will be completed by 17-04-2026 Display Need to add.
23 | M-710iD/70 | AI Palletizing Cell | 46129 | TANUSHREE | AAYUSH | Box sticker deisgn need to release | Box sticker deisgn need to release | • Component replacement needed | Component replacement will be completed by 17-04-2026 Display Need to add. | Box sticker deisgn need to release | Box sticker deisgn need to release
24 | M-2iA/35L | High Speed Primary Packaging Cell |  | DHIRAJ | KARTHIK | Programming support requested to Expert team, waiting for reply | Programming support requested to Expert team, waiting for reply | • Set up needs to be completed | Programming support requested to Expert team, waiting for reply Display Need to add. | Programming support requested to Expert team, waiting for reply | Programming support requested to Expert team, waiting for reply
25 | CRX-10iA/L | RTVT | 46115 | AAYUSH | HARISH | Camera is received, Assembly will be completed in 13-05-2026. Programming will be completed by 27-04-2026 | Camera is received, Assembly will be completed in 13-05-2026. Programming will be completed by 27-04-2026 | • Waiting for camera Solenoid valve replacement | Camera is received, Assembly will be completed in 13-05-2026. Programming will be completed by 27-04-2026 | Camera is received, Assembly will be completed in 13-05-2026. Programming will be completed by 27-04-2026 | Camera is received, Assembly will be completed in 13-05-2026. Programming will be completed by 27-04-2026
26 | M-10iD 12 | Robotic Grinding Cell |  | KARTHIK | TANUSHREE | Details need to collect from design team for additional requirement. | Details need to collect from design team for additional requirement. | • Chennai (vendor contact coordination pending) • Check & Dispatch | Details need to collect from design team for additional requirement. | Details need to collect from design team for additional requirement. | Details need to collect from design team for additional requirement.
27 | R2000iC | Dispensing Cell | 46150
28 | LR Mate 200iD/7L? If not available LR Mate 200iD/4S | Vibrator Sorting cell | 46150
Decapitalization Ringi need to rise by Arunkumar
Fusion Hub
S.No. | Robot Model | Application |  | Primary | Secondary | Remarks | Remarks | Remarks | Remarks | Remarks | Remarks
27 | Arc Mate 120iD | Adaptive Aluminium Welding Cell |  | Kaushik Golla | Ciril Joy Kochu T | Need approval from @Michael & @Rengarajan Sir. | Need approval from @Michael & @Rengarajan Sir. | • Set up needs to be moved | Need approval from @Michael & @Rengarajan Sir. | Need approval from @Michael & @Rengarajan Sir. | Need approval from @Michael & @Rengarajan Sir.
28 | Arc Mate 100iD | Adaptive Arc Welding System |  | Ciril Joy Kochu T | Himanshu Sharma | Need approval from @Michael & @Rengarajan Sir. | Need approval from @Michael & @Rengarajan Sir. | • Set up needs to be moved | Need approval from @Michael & @Rengarajan Sir. | Need approval from @Michael & @Rengarajan Sir. | Need approval from @Michael & @Rengarajan Sir.
29 | CRX-10iA/L | Collaborative Arc Welding System |  | Himanshu Sharma | Roshan S | Need approval from @Michael & @Rengarajan Sir. | Need approval from @Michael & @Rengarajan Sir. | • Set up needs to be moved | Need approval from @Michael & @Rengarajan Sir. | Need approval from @Michael & @Rengarajan Sir. | Need approval from @Michael & @Rengarajan Sir.
30 | CRX-3iA | Collaborative Arc Welding System |  | Roshan S | Ekamjit Singh | Need approval from @Michael & @Rengarajan Sir. | Need approval from @Michael & @Rengarajan Sir. | • Set up needs to be moved | Need approval from @Michael & @Rengarajan Sir. | Need approval from @Michael & @Rengarajan Sir. | Need approval from @Michael & @Rengarajan Sir.
General Item Procurment for TC All Cells
S.No. | Cell | Item |  | Primary | Secondary | Remarks | Remarks | Remarks | Remarks | Remarks | Remarks
1 |  | Experience Center - Side covers |  |  |  | Design is required | Design is required | Design is required | Design is required | Design is required | Design is required
2 |  | Name plate sticker
3 |  | Cable tray - White |  |  |  | Design is requred | Design is requred | Design is requred | Design is requred | Design is requred | Design is requred
4 |  | Polycarbonate fence requirement
5 |  | Safety Fence requirement
6 |  | Pendrive
7 |  | Safety Fence with wheel
8 |  | TC Display with stand
9 |  | Storage Trays
10 |  | AMR Cell - EOAT |  |  |  | Design is required | Design is required | Design is required | Design is required | Design is required | Design is required
11 |  | AMR Cell - TP bracket |  |  |  | Design is required | Design is required | Design is required | Design is required | Design is required | Design is required
12 |  | AMR Cell - P&P assembly |  |  |  | Design is required | Design is required | Design is required | Design is required | Design is required | Design is required
13 |  | Arc Welding cell - Wheel mounting bracket |  |  |  | Design is required | Design is required | Design is required | Design is required | Design is required | Design is required
14 |  | CRX paint cell - Component re-coating |  |  |  | Coating details required | Coating details required | Coating details required | Coating details required | Coating details required | Coating details required
15 |  | Paint cell - Car body Component re-coating |  |  |  | Coating details required | Coating details required | Coating details required | Coating details required | Coating details required | Coating details required
16 |  | Paint cell - EOAT with UV Light need to plan |  |  |  | Need to discuss | Need to discuss | Need to discuss | Need to discuss | Need to discuss | Need to discuss
17 |  | Safety & Insruction magnetic Name plate
18

## Sheet1 (hidden)
1 | CRX-10iA/L | CRX-Paint Cell | 46142 | • Component recoating - Need to send for re-coating Display Need to plan Monitor need to plan | Material Code | Short Name | Qty |  | Remark
2 | P50iB/10L | Paint Cell | 46120 | • New component, recoating - Need to send for re-coating • EOAT - UV light need to plan | ME-WHITE PAINT | DECO WHITE PAINT AS PER SPECs. | 2 | Liter
[5 empty] | ME-THINNER | DECO THINNER | 2 | Liter
[5 empty] | ME-PRIMER | DECO PRIMER | 2 | Liter
[5 empty] | ME-LOCKER | DECO LOCKER | 2 | Liter
[5 empty] | ME-PHOTOCHROMIC POWDER | Pigment powder, as per spec | 2 | https://amzn.in/d/9rIX4Rv | Red Colour
[5 empty] | ME-PHOTOCHROMIC POWDER | Pigment powder, as per spec | 3 | https://amzn.in/d/9rIX4Rv | Yellow colour